## Sheet1
INDEPENDENT NATIONAL ELECTORAL COMMISSION
STRATEGIC PROGRAMME OF ACTION FOR 2012 - 2016
Objective One: To provide electoral operations, systems and infrastructure to support delivery of free, fair and credible elections
S/N | OBJECTIVES | ACTIVITIES | INDICATORS | TIME FRAME |  |  |  | IMPLEMENTING DEPT(S)
|  |  |  | 2013 | 2014 | 2015 | 2016 | LEAD | COLLABORATING
1.1 | Ensure a good constitutional and legal framework for the conduct of free, fair and credible elections | Articulation of areas of amendment to the Constitution / Electoral Act on Political Parties | Proposed areas of amendment completed by Q4 2012 | Q1-Q4 | n.a | n.a | n.a | LS | EPM,EOPS
|  | Undertake necessary legal reforms to allow deployment of modern equipment (including EVMs) in elections | Draft amendment to the Electoral Act ready by Q2, 2014 | Q1-Q4 | Q1-Q4 | n.a | n.a | LS | ICT,EOPS
|  | Policies to allow Out of Country Voting (OCV) and marginalised groups | Proposed areas of Constitutional and Electoral Act amendments completed by Q2 2013 | Q1-Q4 | n.a | n.a | n.a | LS | EOPS
1.2 | Ensure that there is a comprehensive Register of Voters that is accurate and regularly updated | Selection and purging of DDC machines for Continuous Voter Registration exercise | Staff for purging exercise deployed by Q1 2013, 2014,2015 & 2016 | Q1 | Q1 | n.a | Q1 | ICT | VR, State Offices
|  | Identification & procurement of materials for CVR (Deployment of men & materials inclusive) at designated centres | Approval for acquisition secured by Q1 2013, 2014 & 2016, men & materials deployed along | Q1-Q4 | Q1-4 | n.a | Q1-4 | EOPS | Proc, VR,ICT, and State Offices
|  | Technical training of personnel for nation wide Continuos Voter Registration exercise | Approval for training programme secured by Q1 2013, 2014 & 2016 | Q1-Q4 | Q1-Q4 | Q3-Q4 | Q1-Q4 | VR | ICT,TEI, EOPS
|  | Operationalisation of call centre for the Continuous Voter Registration exercise | Consultant hired by Feb. 2013 | Q1-Q4 | Q1-Q4 | Q3-Q4 | Q1-Q4 | I CT | VR
|  | Training of selected monitors from the headquarters on monitoring techniques | Selected monitors/Desk officers trained by Q1 each year | Q1 | Q1 | Q1 | Q1 | EPM | PM, Development Partners/ TEI
|  | Supervision of the CVR exercise | Approval for supervision secured by Q1 2013, 2014, Q4 2015 & Q1 2016 | Q1-Q4 | Q1-Q4 | Q3-Q4 | Q1-Q4 | VR | EOPS, PM, and ICT
|  | Compliance monitoring of (CVR) exercise | Approval secured & monitors deployed upon commencement of the exercise | Q1-Q4 | Q1-Q4 | Q3-Q4 | Q1-Q4 | PM | VR, ICT, EOPS, VPGCL
|  | Display of register of voters at the PUs | Approval secured by Q1 2014, 2015 & 2016 | Q1 | Q1 | Q1 | Q1 | EOPS | ICT, VR,VE, and VPGCL and State Offices
|  | Supervision of Claims and Objections process | Approval secured by Q1 each year | Q1 | Q1 | Q1 | Q1 | VR | PM,ICT, EOPS, State Offices
|  | Compliance monitoring of Claims and Objections | Approval secured by Q1 each year | Q1 | Q1 | Q1 | Q1 | PM | VR, State Offices
|  | Operations security for CVR exercise | Approval secured by Q1 each year | Q1 | Q1 | Q1 | Q1 | EOPS | VR,ICT and State Offices
|  | Updating of ERV Database | Approval secured by Q4 each year | Q4 | Q4 | Q4 | Q4 | ICT | VR
|  | Provision of Disaster Recovery plan and systems for data | Consultant hired by Feb. 2013 each year | Q1 | Q1 | Q1 | Q1 | ICT | VR
|  | Consolidation and integration of the CVR data into the National Register of Voters | Staff deployed to States for the consolidation of CVR data by Q1 each year | Q1 | Q1 | Q1 | Q1 | ICT | VR, State Offices
|  | Prinitng of register of voters for elections | Award of contract for consumables completed by Q2 each year | Q4 | Q4 | Q4 | Q4 | VR | Proc, LS
|  | Printing of Register of Voters into hard drives for Political Parties as mandated by the Electoral Act 2010 (as Amended) | Contract awarded for consumables by Q1 each year | Q1 | Q1 | Q1 | Q1 | VR | ICT
|  | Printing and distribution of Permanent Voters Cards | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ICT | VR and State Offices
|  | Acquire EVM for pilot scheme | Approval secured by Q1 2014 | Q1-Q2 | n.a | n.a | n.a | ICT | EOPS, VR and Proc
|  | Compliance monitoring of Printing of PVCs, data consolidation & functionality of ICT platform | Approval secured & monitors deployed upon commencement of the activity | Q1- Q4 | Q1-Q4 | Q1- Q4 | Q1-Q4 | PM | ICT/VR
|  | Harmonization of Register of Voters with NIMC database | Approval secured by Q4 2015& 2016 | Q4 | Q4 | Q4 | Q4 | ICT | VR
1.3 | Improve ICT deployment and utilisation | Integration of GIS with the Register of Voters | Engagement of contractor by Q1 2013 | Q1-Q2 | n.a | n.a | n.a | VR | EOPS, ICT, LS and State Offices
|  | Implementation and support of web based voter register verification system | Engagement of contractor by Feb. each year | Q1 | Q1 | Q1 | Q1 | VR | ICT
|  | Development of e-library | Approval obtained by Q1 2013 | Q1-Q2 | n.a | n.a | n.a | TEI | ICT
|  | Disaggregation of data by sex in all Commission Electoral Activities e.g. Register of Voters, election results etc. | Template for data disaggregation ready by Q1 each year | Q1-4 | Q1-4 | Q1-4 | Q1-4 | VR | VPGCL, ICT, LGA Offices and TEI
|  | Maintenance of Office Equipment | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Proc | HRM, ICT,VR and State Offices
|  | Integration of INEC Website with voters registry and other INEC database | Contract awarded by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ICT | VR,VPGCL,EOPS
|  | Expansion of INEC mail system to States and upgrade of existing mail server | Contract awarded by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ICT | VPGCL,State Offices
|  | 3M based file tracking system website | Award of contract by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ICT | VPGCL
|  | Provision and upgrade of internet bandwidth service for the Web Unit | Award of contract by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ICT | VPGCL
|  | Provision of external back-up for security of the website | Award of contract by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ICT | VPGCL
|  | Procurement of Card Reader for verification and authentication of Voters | Contract awarded by Q2 2013 | Q4 | Q1, Q4 | Q1 | n.a | ICT | EOPS,Proc
|  | Computerization of staff records and the Commission Registry | Engagement of ICT vendors by March, 2014 | n.a | Q1-Q4 | n.a | n.a | HRM | ICT
|  | Implementation of system application standards in INEC Offices Nationwide | Award of contract for software by Q2 2013 | Q2- Q4 | Q2- Q4 | Q2- Q4 | Q2- Q4 | ICT | All Departments, State Offices
|  | Implementation of Document Management System | Approval secured by Q1 2013, 2014 | Q1- Q4 | Q1- Q4 | n.a | n.a | ICT | All Departments, State Offices
|  | Design of e-election collation System | Approval secured by Q1 2013, 2014 | Q1- Q4 | Q1- Q4 | n.a | n.a | ICT | All Departments, State Offices
|  | Business Process System | Approval secured by Q1 2013, 2014 | Q1- Q4 | Q1- Q4 | n.a | n.a | ICT | All Departments, State Offices
|  | Fleet Management System | Approval secured by Q1 2013, 2014 | Q1- Q4 | Q1- Q4 | n.a | n.a | ICT | All Departments, State Offices
|  | Improvement of communication links between the Commission Hqtrs, States and LGAs for better result transmission during elections | Contract awarded by Q1 2013 | Q1-Q4 | Q1-Q4 | n.a | n.a | ICT | EOPS,Proc
|  | Extension of terrestrial network bandwidth to the LGAs & RAs | Contract awarded by Q2 2013 | Q3-Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | ICT | Proc
1.4 | Undertake proper constituency review of delimitation in line with Constitutional and Electoral provisions | Review of constituencies delimitation nationwide | Approval secured for review exercise by Q1 2013 | Q1-Q4 | Q1-Q3 | n.a | n.a | EOPS | LS, ICT,VR,VPGCL and State Offices
|  | Geo-referencing and mapping of delimitation data including constituencies, state offices, LGAs offices, collation centres, RACs, RAs and PUs | Contract awarded by Q1 2013 | Q2-Q4 | Q1-Q3 | n.a | n.a | EOPS | ICT,VR
|  | Review of RAs, RACs, Collation Centres, PUs etc | Approval secured by Q2 2013, Q1 2014 | Q2-Q4 | Q1-Q3 | n.a | n.a | EOPS | ICT,VR
|  | Compliance monitoring of review of constituencies delimitation nationwide | Approval secured upon the commencement of the review for delimitation exercise & monitors deployed by Q1 2013 | Q1 - Q4 | n.a | n.a | n.a | PM | EOPS, VPGCL
1.5 | Establish an effective and transparent election complaints and dispute resolution mechanism | Creating awareness of Electoral Dispute Resolution mechanism for resolving electoral disputes | Approval for conduct of awareness programme secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADR | EPM, VPGCL
|  | Increased access to justice by the use of EADR for the resolution of electoral disputes | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADR | VE, EPM, HRM,VPGCL
|  | Securing the buy – in and support of stakeholders in the resolution of electoral disputes using mechanisms developed specially under the EADR programme of INEC | Approval for programmes secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADR | The Judiciay, Bar Association, CSO's, NGO's , Donor Partners
|  | Collection and Collation of data and records of disputes on electoral activities | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADR | EPM, EOPS, LS
|  | Printing of manual & guide EADR and workplace mediation guide | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADR | Development Partners
|  | Review/Analysis of the structure & processes of the Constitutions of Political Parties to facilitates ADR | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADR | EPM, Political Parties, LS
|  | Develop framework necessary to manage various types of disputes and varying approaches to resolution | Template / guidelines for dispute resolution ready by Q1 2013 | Q1 | n.a | n.a | n.a | ADR | Development Partners
1.6 | Improved Electoral Processes, Procedures and Systems | Improvement of election results management system | Approval secured by Q2 2013 | Q2-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EOPS | ICT, VR, TEI
|  | Revision of Referendum procedures | Approval secured by Q2 2013 and Q1 in 2014 and 2016 | Q2-Q4 | Q1-Q4 | n.a | Q1-Q4 | EOPS | LS
|  | Review of voting procedure for improved use of technology | Trial runs conducted by Q1 2014 | Q3-Q4 | Q1-Q4 | n.a | n.a | EOPS | ICT,VR,VPGCL,State Offices
|  | Review of RAs and PUs | Approval secured by Q2 2013 and Q1 in 2014, 2015 and 2016 | Q2-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EOPS | ICT,VR,VPGCL
|  | Development of Standard Operational Guidelines for recruitment and deployment of electoral officials. | Approval secured by Q1 2013 | Q1-Q4 | n.a | n.a | n.a | EOPS | LS
|  | Creating an electronic database of deployment list of election officials, including security personnel | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EOPS | ICT,PM and State Offices
|  | Establishment of a system for archiving and analysis of data | Approval secured by Q3 2013 | Q3 | Q4 | n.a | n.a | ICT | EOPS, Proc and State offices
1.7 | To provide infrastructure to support delivery of free, fair and credible elections | Procurement and distribution of appropriate and adequate quantities of election materials for 2013 FCT Area Councils | Processes leading to the award of contract completed by Jan. 2013 | Q1 | n.a | n.a | n.a | EOPS | LS, EPM, Proc
|  | Provide adequate and appropriate transportation for movement of electoral personnel to all levels of operations | Approval secured & deployment plan / template ready for movement of men & material by Q1 2015 | n.a | n.a | Q1-Q4 | n.a | EWT | EOPS
|  | Repair and servicing of Commission's vehicles/boats in preparation for Governorship elections in Ekiti, Anambra and Osun States | Processes leading to the award of contract for servicing & repairs of vehicle and boats completed by Q1 2014 & 2016 | n.a | Q1-Q4 | n.a | Q1-Q4 | EWT | EOPS
|  | Procurement of adequate elections materials for bye-elections and recalls | Contract awarded by Q1 2013, 2014 & 2016 | Q1- Q4 | Q1- Q4 | n.a | Q1- Q4 | EOPS | Proc, LS
|  | Procurement of operational vehicles for Commission Members and RECs | Contract awarded by Q1 2014, and Q1 2015 | n.a | Q2 | Q2 | n.a | EWT | Proc, State offices
|  | Provision of voting cubicles and infrastructures at all Polling Units for physically challenged person | Contract awarded & completed by Q2 2014 | n.a | Q1- Q4 | n.a | n.a | EOPS | Proc, LS
|  | Conduct of 2013 FCT Area Council elections | Approval for conduct of FCT Area Councils election granted by Q4 2012 | Q1 | n.a | n.a | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of FCT Area Council elections | Contracts awarded & completed by Q4 2012 | Q1 | n.a | n.a | n.a | EOPS | Proc
|  | Electoral field operations for conduct of FCT Area Council elections | Approval for personnel and other related costs secured by Q4 2012 | Q1 | n.a | n.a | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of Governorship election in Anambra State | Approval for conduct of the Governorship election granted by end of Q3 2013 | Q4 | n.a | n.a | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of Governorship election in Anambra State | Contracts awarded & completed by Q3 2013 | Q2-Q3 | n.a | n.a | n.a | EOPS | Proc
|  | Electoral field operations for conduct of Anambra State Governorship election | Approval for personnel and other related costs secured by Q3 2013 | Q2-Q3 | n.a | n.a | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of Governorship election in Osun State | Approval for conduct of Anambra State Governorship election granted by Q1 2014 | n.a | Q2 | n.a | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of Governorship election Osun State | Contracts awarded & completed by end of Q1 2014 | n.a | Q1-Q2 | n.a | n.a | EOPS | Proc
|  | Electoral field operations for conduct of Osun State Governorship election | Approval for personnel and other related costs secured by Q1 2014 | n.a | Q1-Q2 | n.a | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of Governorship election in Ekiti State | Approval for conduct of the Governorship election granted by Q2 2014 | n.a | Q3 | n.a | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of Governorship election Ekiti State | Contracts awarded & completed by end of Q2 2014 | n.a | Q2-Q3 | n.a | n.a | EOPS | Proc
|  | Electoral field operations for conduct of Ekiti State Governorship election | Approval for personnel and other related costs secured by Q2 2014 | n.a | Q2-Q3 | n.a | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of 2015 General elections | Approval for conduct of 2015 General election granted by Q4 2014 | n.a | Q4 | n.a | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of 2015 General elections | Contracts awarded & completed by end of Q4 2014 | n.a | Q3-Q4 | n.a | n.a | EOPS | Proc
|  | Electoral field operations for conduct of 2015 General elections | Approval for personnel and other related costs secured by Q4 2014 | n.a | Q3-Q4 | n.a | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of Governorship elections in Bayelsa and Cross River States | Approvals for conduct of Bayelsa and Cross River States Governorship elections granted by Q3 2015 | n.a | n.a | Q4 | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of Governorship election in Bayelsa and Cross River States | Contracts awarded & completed by end of Q2 2015 | n.a | n.a | Q2-Q3 | n.a | EOPS | Proc
|  | Electoral field operations for conduct of Bayelsa and Cross River States Governorship election | Approval for personnel and other related costs secured by Q2 2015 | n.a | n.a | Q2-Q3 | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of Governorship election in Kogi State | Approval for conduct of Kogi State Governorship election granted by Q2 2015 | n.a | n.a | Q3 | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of Governorship election in Kogi State | Contracts awarded & completed by end of Q2 2015 | n.a | n.a | Q2-Q3 | n.a | EOPS | Proc
|  | Electoral field operations for conduct of Kogi State Governorship election | Approval for personnel and other related costs secured by Q2 2015 | n.a | n.a | Q2-Q3 | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of Governorship election in Edo State | Approval for conduct of Edo State Governorship election granted by Q2 2016 | n.a | n.a | n.a | Q3 | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of Governorship election in Edo State | Contract awarded & completed by end of Q2 2016 | n.a | n.a | n.a | Q1-Q2 | EOPS | Proc
|  | Electoral field operations for conduct of Edo State Governorship election | Approval for personnel and other related costs secured by Q2 2016 | n.a | n.a | n.a | Q1-Q2 | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of Governorship election in Ondo State | Approval for conduct of Ondo State Governorship election granted by Q3 2016 | n.a | n.a | n.a | Q4 | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of Governorship election in Ondo State | Contracts awarded & completed by end of Q3 2016 | n.a | n.a | n.a | Q2-Q3 | EOPS | Proc
|  | Electoral field operations for conduct of Ondo State Governorship election | Approval for personnel and other related costs secured by Q3 2016 | n.a | n.a | n.a | Q2-Q3 | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Conduct of 2016 Area Councils election in FCT | Approval for conduct FCT Area Councils election granted by Q4 2015 | n.a | n.a | Q4 | n.a | EOPS | VR,ICT,EPM,NYSC, Federal Agencies and Stste Office
|  | Procurement of election materials for the conduct of FCT Area Councils election | Contracts awarded & completed by end of Q4 2015 | n.a | n.a | Q3-Q4 | n.a | EOPS | Proc
|  | Electoral field operations for conduct of FCT Area Councils election in 2016 | Approval for personnel and other related costs secured by Q4 2015 | n.a | n.a | Q2-Q3 | n.a | EOPS | TEI, VR,ICT,VPGCL EWT
|  | Improving operational readiness of Zonal Stores | Contracts awarded by Q1 each year | Q1- Q4 | Q1- Q4 | n.a | n.a | EOPS | Zonal Stores
|  | Retrieval of used & unused balloting materials | Approval secured by Q3 2015 | n.a | n.a | Q3-Q4 | n.a | EOPS | EWT, State Offices
|  | Provision & Installation of baggage scanner at the Commission's Headquarters | Contract awarded by Q1 2013 | Q1 | n.a | n.a | n.a | Secuirty | EWT
|  | Installation of electronic iron barrier riser at the Commision's headquarters main gate | Contract awarded by Q3 2013 | Q3 | n.a | n.a | n.a | Secuirty | ICT
|  | Construction of observatory posts (3 Nos.) at the Commission's headquarters | 3 Nos. observatory posts erected by Q1 2014 | n.a | Q2 | n.a | n.a | Secuirty | EWT
|  | Installation of Infrared Intrusion Detection Devices at the Commission's Hqrts. | Contract awarded by Q1 2013 | Q1 | n.a | n.a | n.a | Secuirty | EWT
Objective Two: To improve voter education, training and research
S/N | OBJECTIVES | ACTIVITIES | INDICATORS | TIME FRAME |  |  |  | IMPLEMENTING DEPT(S)
|  |  |  | 2013 | 2014 | 2015 | 2016 | LEAD | COLLABORATING
2.1 | Formulate and Implement Voter Education Programme | Integration and implementation of Voter Education in the secondary school and Terrtiery Institution | Integrations arrangement commence by Q1 2013 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | TEI
|  | Conduct Voter Education in Secondary Schools and Institions | MoU signed between INEC and collaborating Agencies | Q2 - Q4 | Q2 - Q4 | Q1 | n.a | VPGCL | TEI
|  | Workshops and Retreats on Voter Education for 2015 Elections by NICVE | Workshops & retreats conducted by Q2 each year | Q2-Q4 | Q2-Q4 | Q2-Q4 | Q2-Q4 | VPGCL | TEI, Development Partners
|  | Implementation of Voter Education in collaboration with NICVE | Voter education programmes on CVR conducted by Q1 each year | Q1- Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | TEI
|  | Erection of bill boards for enlightment | Contract awarded Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | Proc, LS
|  | Printing of voter education materials | Contract awarded by Oct. 2013 & Feb. 2014 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | Proc, LS, Development Partners
|  | Organise voter education fora for the followings: Traditional Institutions, Religious Groups & Faith Based Institutions, Labour Unions, Professional Groups, Market Persons, Academic Communities and Non-Influential Groups, Youth Groups, and Voter Education Providers. etc | Fora conducted between Q1-Q4 2014 , 2015 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | TEI
|  | LGA and RA level Voter Education programme for Stakeholders | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | State & LGA offices
|  | State level Voter Education Fora by RECs for election Stakeholders in the 36 States & FCT | Approval for conduct of fora secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | State Offices
|  | Sensitization of voters through mobile phones SMS | Approval secured and arrangement with GSM providers completed by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | Service Providers
|  | Procurement of 18 new landrover Cine Rovers for public enlightment | Contract awarded by Feb. 2015 | n.a | n.a | Q1 |  | EWT | VPGCL, Proc
|  | Compliance monitoring of Voter Education Activities | Approval secured to monitor the voter education activities upon commencement | Q1-Q4 | Q1-Q4 | Q1-Q2 | Q1-Q2 | PM | VPGCL,ADR
|  | Adoption and implementation of INEC Gender policy | Launching of the Gender policy by Q1 2013 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | All Departments, State Offices
|  | Development and Printing of TEI Handbook on its programmes | Contract awarded for Printing of TEI Handbok by Q2 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | TEI | VPGCL
|  | Rejuvenation of quarterly Electoral Magazines | Production by Q1 each year | Q1 - Q4 | Q1 - Q4 | Q1 - Q4 | Q1 - Q4 | VPGCL | All Departments
2.2 | Formulate and Implement Training Programmes | Training of INEC staff and Observers on monitoring of political party conventions, congresses and primaries | Training conducted by Q1 each year | Q1, Q3 | Q1, Q4 | Q1, Q3 | Q1, Q3 | EPM | TEI,LS
|  | Refresher Courses for officers & supervisors (Over-Sea Courses) | Institution identified and approval secured by end of Q1 each year | Q1- Q3 | Q1- Q3 | Q1- Q3 | Q1- Q3 | Secuirty | HRM
|  | BRIDGE modular training for State Civil Society Desk Officers | Consultant hired by Q2, 2013 | Q2 | n.a | n.a | n.a | VPGCL | State Offices
|  | BRIDGE modular training for INEC Staff on electoral dispute resolution | Consultant engaged by Q2 each year | Q2 -Q3 | Q2 -Q3 | Q2 -Q3 | Q2 -Q3 | ADR | TEI, Development Partners
|  | Training of CSOs in the 36 States and the FCT on gender issues | Approval for training secured by Q1 2013 and Q2 2014 | Q1 | Q2-Q3 | n.a | n.a | VPGCL | TEI
|  | Pre-retirement workshop for all INEC Staff | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Pensions Unit | HRM, F/A, and State Offices
|  | Workshop on planning for retirement | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Pensions Unit | HRM, F/A, and State Offices
|  | Capacity building for INEC Pension Unit Staff | Approval secured by Q3 2013, 2014 and 2016 | Q3 | Q3 | n.a | Q3 | Pensions Unit | F/A, HRM and State Offices
|  | Sensitization of accredited election observers & training of election monitors on constituency delineation | Proposal/training sensitization workshop for monitors and observers ready by Feb. 2013 | Q2 | n.a | n.a | n.a | EPM | EOPS, TEI
|  | Training of Poll Officials for 2013 Governorship election in Anambra State | Approval secured by Q3 2013 | Q3 | n.a | n.a | n.a | TEI | NYSC and Federal Agencies
|  | Training of Poll Officials for 2015 General Elections | Approval secured by Q1 2015 | n.a | n.a | Q1 | n.a | TEI | EOPS,NYSC, State Offices and Federal Agencies
|  | Conduct of Training Needs Analysis (TNA) for staff | Consultant hired by April each year | Q1-Q3 | Q1-Q3 | Q1-Q3 | Q1-Q3 | TEI | Development Partners and State Offices
|  | Review of election manuals to accommodate persons with disabilities | Approval secured by Q1each and training conducted by Feb. 2013, 2014 | Q1-Q2 | Q3-Q4 | n.a | n.a | TEI | EOPS, LS, Development Partners
|  | Procurement of multimedia Interactive Training Kits and equipment | Contract awarded by April 2013 | Q1-Q2 | Q3-Q4 | n.a | n.a | TEI | Proc
|  | Capacity building of staff through for attendance of relevant courses and workshops, both local and international | Engagement of management consultants by Q2 each year | Q2 | Q2 | Q2 | Q2 | HRM | All Deparments and State Offices
|  | Induction workshop for newly recruited officers | Approval secured by Q1 2013 | Q1-Q2 | n.a | n.a | n.a | HRM | EOPS,ICT,VR
|  | Training on Operating System, DBMS, and Development tools that support the Voter register | Engagement of IT firms by January each year | Q1 | Q2 | Q3 | Q4 | VR | ICT,TEI
|  | Sensitisation workshops on manual & guide for EADR workplace mediation guide | Approval secured within Q1-Q4 each year | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | ADR | Development Partners
|  | Quarterly Lecture Series, Conferences, Seminars and Workshops on electoral and political parties dispute | Approval secured by Q1 each year | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | ADR | EPM, Political Parties, Development Partners
|  | Training of INEC Staff/University academic and Staff of FTIs on e-collation | Capacity building for election officials | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | TEI | ICT,EOPS
|  | Production of bi-annual Nigeria Electoral Journal for publcation on research studies on democarcy and electoral process | Journal published by Q2 and Q4 each year | Q2, Q4 | Q2, Q4 | Q2, Q4 | Q2, Q4 | TEI | All Departments
|  | Training of Public Affairs Officers, EOs, AEOs,CSOs and NOA on implementing Voter Education at the local levels | Approval secured for capacity building by Q2 2013 and Q1 2014 | Q1-Q4 | Q2- Q4 | n.a | n.a | VPGCL | TEI
2.3 | Formulate and implement a research agenda | Conclusion of study on 2011 elections & publication of same | Submission of Findings of Study to the Commission by April 2013 and Presentation of Findings to Stakeholders by June 2013 | Q1, Q2 | n.a | n.a | n.a | TEI | EPM, Resource Persons External
|  | Study on Profile of National Assembly Members and State House of Assemly Members | Proposed approval secured by Q1 2013 | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | TEI | Resource Persons External
|  | Completion of Study on Democratization at the Grassroots &Publication of same | Findings of study presented to Commission by May 2013 and Report printed by June 2013 | Q1, Q2 | n.a | n.a | n.a | TEI | Resource Persons External
|  | Capacity enhancement of Research Officers; and study visits to other EMBs | Specific training programmes & training institutions identified by Feb. each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | TEI | HRM
|  | Translation of Nigerian Constitution, Electoral Act, 2010 and other INEC Publications into local Nigerian Languages for voter education and information | Recruitment of professional translators and production of materials from translated document completed by Q1, 2013 and Q2, 2014 | Q1-Q4 | Q1-Q4 | n.a | n.a | TEI | LS, VPGCl and Language Institutions
|  | Collection and interpretation of proverbs and world views in 12 selected Nigerian Languages | Draft report submitted to the Commission by Q1 2013 | Q1-Q4 | n.a | n.a | n.a | TEI | External Resource Persons
|  | Collaboration with Researchers from Nigerian Universities to undertake the Studies on preparations, issues,conduct and outcomes of the 2015 general Elections and Publication of same | Recruitment of Resource persons by June 2014, Documentation of activities in the elections in all states of federation and FCT by June 2014, Producing Report on the study by Q4 2015, Presentation of findings to the Commission- and other stakeholders. by June 2016 | Q2 | Q1, Q2 | Q1-Q4 | Q1, Q2 | TEI | External Resource Persons
|  | Presentation of papers and research studies at International seminars and conferences | Research officers participate in international conferences and seminars particularly in such organized by foreign universities regularly | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | TEI | External Resource Persons
|  | Recruitment of new staff to beef up staff strength at the L.G.A | Engagement of management consultants by Q1 2013 | Q1, Q2 | n.a | n.a | n.a | HRM | State Offices, Federal Character Commission
|  | Creation and update of Election Officials Databank | Approval for study secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | TEI | EOPS, LS, VPGCL, EPM, State Offices External Resource Persons
|  | Clinical reference books for Doctors/ Nurses | Contract awarded by Q1 2013 | Q2 | n.a | n.a | n.a | Health Services | TEI
2.4 | Institutionalise the National Inter-Agency Committee on on Voter Education | Institutionalise National Inter Agency NICVE inagurate Committee on Voter Education | NICVE inangurated by March 2013 | Q1 | n.a | n.a | n.a | VPGCL | NBC,NOA,FRCN,NCC,GSM Providers such as MTN,Glo, Airtel, Etsalat etc.
2.5 | Formulate and implement policies to ensure participation of marginalised groups including persons with disability as well as Out of Country Voting (OCV) | Enhance the participation of Persons Living with Disabilities(PLWD) as well as Out of Country Voting (OCV) on the electoral process | Approval secured for conduct of zonal workshops by Q2 2013, 2014 & Q1 2015 | Q2 | Q3 | Q1 | n.a | VPGCL | CSOs, NGOs
Objective Three: To register political parties and monitor their operations
S/N | OBJECTIVES | ACTIVITIES | INDICATORS | TIME FRAME |  |  |  | IMPLEMENTING DEPT(S)
|  |  |  | 2013 | 2014 | 2015 | 2016 | LEAD | COLLABORATING
3.1 | Register political Parties | Registration of political parties | To be in line with Constitutional and Electoral Acts provisions | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | EPM | LS, ADR
|  | Stregthening the conditions for registration of political Parties and ensuring strict compliance | Reviewed guidelines and regulations for party registration ready by Q1 each year | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | EPM | LS, ADR
3.2 | Monitoring the nomination of candidates | Monitoring of political parties primaries and congresses. | All political party primaries, congresses and conventions are monitored upon notification | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | EPM | LS, ADR
|  | Verification of claim of candidates for elections | Templates for verification of claims of candidates in line with election timetable ready by Q1 each year | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | EPM | LS, ADR
|  | Continuous review of procesess to enhance internal party democracy | Three stakeholder meetings/ workshops on internal party democracy Q1 or Q2 each year | Q1- Q2 | Q1- Q2 | Q1 | Q1- Q2 | EPM | LS, ADR
|  | Facilitate resolution of dispute arising from party congresses & conventions | Template for resolution of political dispute ready by Q1 each year | Q1- Q4 | Q1- Q4 | Q1 | Q1- Q4 | ADR | EPM, LS
|  | Computerization of personal particulars of nominated candidates for elections | Approval secured to procure the software & consultants hired to implement by Q2 2013, and Q2 2014 | Q1 – Q4 | Q1 – Q4 | n.a | n.a | LS | ICT
3.3 | Monitoring the finances of Political Parties | Tracking of contributions to Political Parties | Template/Guidelines for tracking ready by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | n.a | EPM | States,LGA Offices
|  | Audit checks on the account of political parties and quarterly submission of financial reports | Audit Firms hired by Q4 each year and report ready by Q1 each year | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | EPM | IA, State, LGA Offices
3.4 | Monitoring of political party campaigns | Senzitization of political parties on the rules of engagement during campaigns | Approval secured by Q3 2014 and Q1 2015 | n.a | Q3- Q4 | Q1 | n.a | EPM | ADR, States and LGA Offices
|  | Design of programmes for monitoring of campaign finances | Approval secured by Q1 2014,2015 & 2016 | n.a | Q1- Q3 | Q1 | Q1 | EPM | ADR, States and LGA Offices
|  | Appointment of monitoring Teams | Approval secured by Q1 2014,2015 & 2016 | n.a | Q1- Q3 | Q1 | Q1 | EPM | States and LGA Offices
3.5 | Tracking of campaign finances of candidates and political parties | Training of INEC Staff and CSOs on tracking of campaign finance | Approval secured by Q3 each year | Q3- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | EPM | IA,LS
|  | Appointment of Teams for tracking campaign finances, including consultants, CSOs INEC staff and application of sanctions where ncessary | Approval secured and Team appointed by Q1 each year | Q3- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | EPM | IA, LS
|  | Collation of campaign budgets submitted to the Commission after parties campaigns | Template for receipt of campaign budget ready by Q1 2014 | n.a | Q1- Q3 | Q1 | Q1 | EPM | IA,LS
3.6 | Monitoring media access | Engagement with NBC and election stakeholders on effective monitoring of media access by political parties/candidates. | Approval secured for conduct of one workshop / seminar by Q4 2013, 2014, Q1 2015 and Q4 2016 | Q4 | Q4 | Q1 | Q4 | EPM | VPGCL
|  | Constitution of election stakeholder forum including NBC on monitoring and tracking of media access | Approval secured and team inaugurated by Q4 2013. | Q4 | n.a | n.a | n.a | EPM | VPGCL
Objective Four: To interact nationally and internationally with relevant stakeholders
S/N | OBJECTIVES | ACTIVITIES | INDICATORS | TIME FRAME |  |  |  | IMPLEMENTING DEPT(S)
|  |  |  | 2013 | 2014 | 2015 | 2016 | LEAD | COLLABORATING
4.1 | Establish a mechanism for regular consultation with stakeholders | Convening of Stakeholders/Forum | Stakeholder forum held in each of the Geo-political zone by Q3 each year | Q2-Q3 | Q2-Q3 | Q2-Q3 | Q2-Q3 | VPGCL | State Offices
|  | Compilation and publishing of monitors and observers reports | Final production ready by first quarter 2016. | n.a | n.a | n.a | Q1 | EPM | VPGCL, TEI
|  | Collaboration with Development Partners and EMBs on areas of mutual benefits | Approval secure by Q1 each year | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | ICP | LS
|  | Interaction with Diplomatic Missions, Foreign Affairs, Customs and Immigration | Arrangement completed by Q3 each year | Q4 | Q4 | Q4 | Q4 | ICP | LS
|  | Cooperation Agreements with some Develeopment Partners and EMBs | Arrangement completed by Q4 each year | Q1- Q4 | Q1- Q4 | Q1- Q4 | Q1- Q4 | ICP | LS
|  | Compilation of Report on technical assisatnce received from Development Partners | Report to be ready by end of Q4 each year | Q1 | Q1 | Q1 | Q1 | ICP | EPM, TEI
|  | Coordination of international observer missions | Arrangement for election day tour completed by Q1 2015 | n.a | n.a | Q1 |  | ICP | EPM,EOPS and TEI
|  | Consolidating bilateral ties with collaborating agencies to encourage electoral commitment | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EPM | EPM, LS, Development Partners and Collaborating Institutions
|  | Secure commitments from traditional rulers, religious leaders, the legislature,Gender based civil society organisation and political parties through advocacy to support women polictical aspirations | Approval secured by Q2, 2013 & Q1,2014 | Q2-3 | Q1-4 | n.a | n.a | VPGCL | State Offices
|  | Enhance political participations of female politicians through round table discussions | Approval secured by Q2 2013 | Q2 | n.a | n.a | n.a | VPGCL | ADR and State Offices
|  | Secure peaceful political space conducive for women & youth political participation with zonal round tables for youths to shun electoral violence. | Six zonal youth conferences / roundtables by Q1, 2013, Q1 2014 & Q1, 2015 | Q1-Q4 | Q1-Q4 | Q1 | n.a | VPGCL | ADR and State Offices
|  | Enhance outreach programmes to market women | Outreach programmes in 2 major markets per State conducted by Q1-Q3 in 2013, 2014 & Q1 2015 | Q1-3 | Q3-4 | Q1 | n.a | VPGCL | ADR and State Offices
|  | Collaboration with SIECs to enhance international best practices through training, workshops and knowledge sharing. | Specific training programme & institutions identified and approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | State Coordination | TEI and Development Partners
|  | Quarterly Lecture Series, Conferences, Seminars and Workshops for Staff | Workshop organized Quarterly each year | Q1 - Q4 | Q1 - Q4 | Q1 - Q4 | Q1 - Q4 | TEI | Secretary's Office, VPGCL
4.2 | Publish a newsletter and periodic workshops/ seminars | Electoral Magazine and Daily Bulletin | Contract awarded a month to release of each edition | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | All Departments
4.3 | Engage election observers | Review of the 2011 General elections and rerun election with observer groups. | Approval for review workshop secured by Dec. 2012. | Q1 | n.a | n.a | n.a | EPM | EOPS,ICP, PM
|  | Observation/ Monitoring of Electoral activities in other Countries | Approval secure one month before the election day | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EPM | PM
|  | A review of observer accreditation process | Draft proposal submitted to the Commission by (Dec. 2012) | Q1 | n.a | n.a | n.a | EPM | EOPS,TEI
|  | A review of the Commissions policy on foreign election observation | Approval for review of the policy on foreign observation secured by Jan. 2013. | Q1 | n.a | n.a | n.a | EPM | Commission
|  | Engagement with international agencies (ECOWAS, AU, etc) on foreign election observation | Approval secured by Q1 2013 | Q1-Q2 | n.a | n.a | n.a | EPM | ICP, IFES/UNDP
|  | Procurement of election observation Kits | Award of contract to supply kits. Ready by Q2 2014 | n.a | Q2 | n.a | n.a | EPM | Proc, LS
|  | Review and production of guidelines for Election Observers | Draft review to be submitted by Feb. 2014 | n.a | Q2 | n.a | n.a | EPM | TEI, EOPS
|  | Establish a mechanism for regular consultation with long term and short term election observers | Policy document to be ready by Q2 2013 | Q2 | n.a | n.a | n.a | EPM | ICP
4.4 | Engage the media | Organise, coordinate media programmes & advert on gender issues and perspectives on Electronic, Print and social media | Approval secured by Q1 each year | Q1-Q2 | Q1-Q3 | Q1 | n.a | VPGCL | TEI
|  | Intensification of jingles production & airing, adverts/announcements handbills, regular talk shows, posters/leaflets documentaries/press briefings/conferences analyses/commentaries, opinions, editorials, etc. | All jingles are ready and contract awarded for materials in Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VPGCL | State Offices
4.5 | Institutionalise the Inter-agency committee on election security through MoU and manuals | Quarterly meeting of Inter-Agency Consultative Committee on Election Security (ICCES) at National level | Approval secured & meetings held quarterly 2013, monthly 2014, and forthnightly 2015 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Seurity | Security Agnecies
|  | Quarterly meeting of Inter-Agency Consultative Committee on Election Security (ICCES) at States level | Approval secured & meetings held quarterly 2013, monthly 2014, and forthnightly 2015 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | RECs Office | Member institution of ICCESS
|  | Quarterly meeting of Inter-Agency Consultative Committee on Election Security (ICCES) at LGAs level | Approval secured & meetings held quarterly 2013, monthly 2014, and forthnightly 2015 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EOs Office | Member institution of ICCESS
|  | Development and production of manual on election duties for security personnel | Draft manual ready by Q2 2013 | Q2-Q4 | Q2-Q4 | n.a | n.a | TEI | EOPS,LGAs Offices, ADR, Security Unit
|  | MoUs signed by INEC with various agencies represented on ICCES | Draft MoU ready by Q1 2013 | Q1 | n.a | n.a | n.a | Seurity Unit | Legal
Objective Five: To re-organise and reposition INEC for sustained conduct of free, fair and credible elections
S/N | OBJECTIVES | ACTIVITIES | INDICATORS | TIME FRAME |  |  |  | IMPLEMENTING DEPT(S)
|  |  |  | 2013 | 2014 | 2015 | 2016 | LEAD | COLLABORATING
5.1 | To enhance institutional capacity for managing election operations smoothly, effectively and efficiently | Exchange Programme for Staff on capacity building | Approval secure by Q2 each year | Q2 | Q2 | Q2 | Q2 | HRM | All Departments
|  | Compliance monitoring of elections, bye elections, referendums, and readiness assurance | Approval Secured when the need arises to conduct elections, bye-elections, | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | EOPS,EPM and ADM
|  | Extension of Planning and Monitoring Unit structure to States | Request for approval of structure in the States & Staff trained by Q2 2013 | Q2- Q3 | Q2- Q3 | n.a | n.a | PM | HRM and State offices
|  | Continuing dispute resolution training( Local & International) for INEC Dispute Resolution Officers | Approval secured by Q2 each year | Q2 – Q4 | Q2 – Q4 | Q2 – Q4 | Q2 – Q4 | ADR | HRM and State offices
|  | Annual Dispute Resolution Review Conference ; deliberation on topical issues and recent trends in Dispute Resolution | Approval secured by Q3 each year | Q3 | Q3 | Q3 | Q3 | ADR | HRM and State offices
|  | Production of EADR guide and Workplace dispute resolution guide as may be needed from time to time for training | Approval secured by Q3 2013, Q1 2014, 2015 and 2016 | Q3 | Q1 – Q2 | Q1 – Q2 | Q1 – Q2 | ADR | HRM and State offices
|  | Acquisition of basic ADR skills by Commission Members and advanced ADR staff training both at the Headquarters and State Offices | Approval secured by Q1 each year | Q1 – Q2 | Q3 | Q1 | Q1 | ADR | HRM
|  | Collaborating with and establishing co-operative relationships with stakeholders and acquiring their buy - in for the purpose of promoting the use of ADR in the resolution of pre-election political disputes | Approval secured by Q3 each year | Q3 | Q3 | Q1 –Q4 | Q3 | ADR | LS, EPM, VPGCL
|  | Creating awareness of workplace mediation in the Headquarters & States towards eventually setting up a Workplace Dispute Resolution Centre | Approval secured by Q2 each year | Q2-Q4 | Q2-Q4 | Q2-Q4 | Q2-Q4 | DR | State Offices
|  | Interface with political parties on rules & procedures for party management | Guidelines and regulations (and review ready by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EPM | LS,ADR
|  | Identification and monitoring of early warning signs of conflict during delimitation of political constituencies, parties campaigns and primaries for intervention | Template for detection of early warning signs on electoral activities ready by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | DR | EOPS, EPM, LS
|  | Ensuring that the internal control mechanisms are implace and working perfectly as approved by the Commission | Audit working materials ready by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | IA | F/A
|  | Conduct of value for money auditing | Approval secured to conduct value for money on Commision projects by Q1-Q4 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | IA | PM, F/A
|  | Annual review of books of accounts and records at Headquarters & State Offices | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | IA | All Departments
|  | Stock taking and assets verification | Approval secured by Q4 each year | Q4 | Q4 | Q4 | Q4 | IA | F/A, State Offices
|  | External audit at the INEC Headquarters, State Offices and Consolidation | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | IA | All Departments
|  | Monitoring of Election Petitions and Appeals | Approval secured to undertake monitoring of election petitions by Q1, 2014 & Q1, 2015 | n.a | n.a | Q1 – Q4 | Q1 – Q4 | LS | ADR
|  | Defence of election petitions | Approval secured by Q1 2015 & Q1 2016 | n.a | n.a | Q1-Q4 | Q1-Q4 | LS
|  | Prosecution of Electoral Offences | Approval secured by Q1 2015 & Q1 2016 | n.a | n.a | Q1-Q4 | Q1-Q4 | LS
5.2 | Improve capacity, communication, co-ordination, training and data management | Capacity Building in Planning, Monitoring & Evaluation for PM Staff (HQrs & States) | Consultant hired to build capacity by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | HRM
|  | Professional Conferences and Mandatory Continuous Education for staff of the Commission | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | HRM | All Departments
|  | Specialised training of Operations Staff on data archiving and analysis | Approval secured by Q3 2013 and Q1 2014 | Q1-Q3 | Q1-Q4 | n.a | n.a | EOPS | ICT,TEI
|  | Workshops, Seminars and Skills development on Election Management | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | n.a | n.a | EOPS | TEI
|  | Training for Procurement Planning | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Proc | HRM
|  | Training / Workshops for Logistics/Operations Officers ON Electoral Operations | Approval secured by Q1 2013, 2014 & 2016 | Q1-Q4 | Q1-Q4 |  | Q1-Q4 | EOPS | HRM,IFES
|  | Workshops, conferences, seminars and International Voter Registration observation | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | VR | TEI
|  | Refresher training on litigation and drafting skills for legal officers. | Legal Officers trained in advocacy and drafting skills by Q1-Q4 each year | Q1 – Q4 | Q1 – Q4 | Q1 – Q4 | Q1 – Q4 | LS | HRM
|  | Human Capital Development on Computer appreciation & application for staff | Staff to participate in training secured by April each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | HRM | ICT
|  | Training on Time Management for effectiveness | Consultant hired by April 2013 & 2014 | Q1-Q4 | Q1-Q2 | n.a | n.a | HRM | All Departments
|  | Training on Stress Management for Executives | Consultant hired by Feb. 2013 | Q1 | Q4 | n.a | n.a | HRM | Health Services
|  | Training on Effective Stores Management Document and Record management | Consultant hired by June 2013, 2014 & Feb. 2015 | Q1-Q4 | Q1-Q4 | Q1 | n.a | HRM | Stores, State offices
|  | Training on Enhancing Productivity through Emotional Intelligence and work ethics for staff | Consultant hired by April 2013 & Feb. 2014 | Q1-Q4 | Q1-Q2 | n.a | n.a | HRM | All Departments
|  | Training on Pension Management and Administration | Consultant hired by Feb. 2013 & Oct. 2014 | Q1 | Q1-Q4 | n.a | n.a | HRM | Pension Unit
|  | Training on Advanced Management for Health Professionals/ Administrators | Consultant hired by March. 2013 & Nov. 2014 | Q1 | Q1-Q4 | n.a | n.a | HRM | Health Services
|  | Training on Application of Crisis Management, Team Building and performance Management techniques | Approval for courses secured by April 2013 & Feb. 2014 | Q1-Q3 | Q1 | n.a | n.a | HRM | All Departments
|  | Training on Strategic Manpower Planning and Development | Training institutions identified and approval secured by April 2013 | Q1-Q4 | n.a | n.a | n.a | HRM | All Departments
|  | Capacity building for Audit Staff at the HQrs & States | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | IA | HRM
|  | Training on Leadership and Motivation | Training institutions identified and apprval secured by June 2013 & Feb. 2014 | Q3-Q4 | Q1 | n.a | n.a | HRM | All Departments and State Offices
|  | Advanced General Management Courses for Management Team | Consultant hired by June 2013 & March 2014 | Q1-Q4 | Q1 | n.a | n.a | HRM | All Departments and State Offices
|  | Training on Speech/Memo Writing | Training institution identified and approval secured in Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | HRM | All Departments
|  | Sponsorship to international study trips on electoral management, to institutes and EMBs | Approval secured by Q2 each year | Q2 | Q2 | Q2 | Q2 | TEI | HRM,Development Partners
|  | Diploma Programme and Post Graduate Diploma in Election Administration in three 3 collaborating premier institutions (ABU, UNN & U.I) | Approval secured by Q1 2013 & 2014 and selected staff sponsored | Q1 - Q2 | Q1 - Q2 | n.a | n.a | TEI | ABU, UNN, UI
|  | Organized workshops on crisis communication | Approval secured by Q4 each year | Q4 | Q4 | Q4 | Q4 | VPGCL | HRM,DR
|  | Capacity building for SERVICOM Staff | Approval Secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADM | All Departments, and State Offices
|  | Creation of awareness and evaluation of service delivery | Approval Secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADM | All Departments, and State Offices
|  | Partnership/ collaboration with development partners on capacity building | Discussion with development partners on areas of collaboration on capacity building finalized by Feb. 2013 | Q1-Q4 | Q1-Q4 | Q1 | Q1-Q4 | EPM | Development Partners,All Departments
|  | Training of party agents, observers and media on electoral process | Approval for conduct of training for party agents, obersvers and media secured by Q1 each year | Q4 | Q1-Q4 | Q1 | Q1 | EPM | VPGCL,TEI
|  | National and International Courses for Medical and Nursing Officers | Institutions identified and approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Health Services | HRM
5.3 | Improve work environment and enhanced team work among the staff of the Commission | Construction of State Headquarters and LGA offices | Contract awarded by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EWT | Proc and State Offices
|  | Construction of RECs Residences. | Contract awarded by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | n.a | EWT | Proc and State Offices
|  | Construction of National Commissioners' residences | Contract awarded by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | n.a | EWT | Proc
|  | Rehabilitation of existing Infrastructure | Contract awarded by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EWT | Proc and State Offices
|  | Maintenance of Headquarters, State Offices and LGA Offices | Contract awarded by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | EWT | Proc and State Offices
|  | Compliance monitoring of Commission Projects: Construction of LGA Offices, National Commissioner's Residences, RECs Residences & Renovation of buildings at the LGA/State/HQrs | Approval secured to monitor the projects upon award of contract | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | IA
|  | General Expansion and furnishing of the Staff Clinics | Contract awarded by Q1 2013, Q1 2014 | Q1-Q4 | Q1-Q4 | n.a | n.a | EWT | Health Services
|  | Construction and renovation of existing structures at TEI Minna Training Center | Award of contract by Q1 2013 | Q1 - Q4 | n.a | n.a | n.a | EWT | TEI
|  | Construction of library, stocking and furnishing of TEI Study Centres at Minna and Oghara | Contract awarded by Q1 2013 & 2014 | Q1 Q4 | Q1 Q4 | Q1 Q4 | Q1 Q4 | TEI | EWT
|  | To provide recreational facilities and centers; To provide sports facilities; To improve the service of the Canteen. | Contract awarded by Q1 2013 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADM | EWT
|  | Engaging developers and mortgage institutions to provide houses to Staff of the Commission | Approval secured by Q2 2013 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | ADM | EWT, Developers and Mortgage Institutions
5.4 | Improve human resources management to meet current and future challenges of INEC | Review the existing staff condition of service | Retreat of Human Resources experts and Commission Members by June 2013 | Q2-Q4 | Q1 | n.a | n.a | HRM | State Offices
|  | Standardization of staff Identification Card Nationwide | Engagement of consultant by Feb. 2013 | Q1-Q4 | Q1-Q4 | n.a | n.a | HRM | ICT,State Offices
|  | Upgrade of PM Networks at the HQrs, Abuja | Contract to be awarded Q1 2013 | Q1-Q4 | n.a | n.a | n.a | PM | ICT
|  | Compliance monitoring of Processes and programmes | Approval secured by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | All Departments
|  | Medical Support Services to election personnel for General elections | Arrangement for medical support services completed by March 2015 | n.a | n.a | Q1 | n.a | Health Services | EOPS
|  | Manpower audit | Approval secured by Q1 each year | Q1-Q4 | n.a | Q1-Q4 | Q1-Q4 | HRM | IA
5.5 | Budget and manage the financial resources of INEC effectively and efficiently | Monitoring implementation of the Strategic Programme of Action | Constitution and inaguration of Plan Comittee by Q1 2013 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | All Departments
|  | Procurement of PM Election Monitors Kits | Contract awarded & completed by Q1 2013 | Q1, Q2 | n.a | n.a | n.a | PM | Proc
|  | Compliance monitoring of budget implementation | Approval to monitor budget implementation commencing Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | F/A
|  | Computerization of the Finance and Account Department Functions in line with Federal Government's policy | Approval secured for acquisition of software by Q2 2013 | Q2 | Q1-Q4 | n.a | n.a | F/A | ICT,PM
|  | Electronic Documentation to meet Financial Regulations on retention of security documents, records and books of accounts after use | Electornic Backup copies of documents, records and books of accounts completed at the end of Q4 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | F/A | ICT
|  | Budgeting and Budgetary control | Realistic Budget and Budget discipline done at the end of each quarter | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | F/A | All Departments
|  | Installation of statutory reporting software in the 36 States and FCT Accounting Units of the Commission (ATRRS Software). | Approval secured by Q1 2013 | Q1-Q2 | n.a | n.a | n.a | F/A | ICT/OAGF
|  | Interactive forum of Insurance and Pension Officers with Pension Fund Administrators nationwide. | Forum to hold by Q2 each year | Q2 | Q2 | Q2 | Q2 | F/A | HRM, Pension Unit
|  | Insurance of Human and Material/Assets of the Commission | Insurance Policies for Staff, Commission Members and all assets of the Commission with premium fully paid by Q1 each year | Q1 | Q1 | Q1 | Q1 | F/A | EWT, ICT
|  | Purchase of utility and other vehicles | Contract awarded to procured 5 Nos. Vehicles by Q1 2013 & Q1 2014 | Q1 – Q4 | Q1 – Q4 | n.a | n.a | EWT | All Departments
|  | Procurement of law Reports, text books and other research materials | Contract awarded to supply books by Q1 each year | Q1 – Q4 | Q1 – Q4 | Q1 – Q4 | Q1 – Q4 | LS | Proc
|  | Production of copies of the Constitution, Electoral Act, Manuals and Guidelines. | Contract awarded by Q4 2013 | Q4 | Q1 | n.a | n.a | LS | Proc
|  | Provision of ICT office equipment at TEI and its Study Centres | Contract awarded by Q1 2013 | Q1-Q4 | n.a | Q1-Q4 | Q1-Q4 | TEI | Proc
|  | Purchase of fire fighting Mini-Truck, fire incident wireless address system and Patrol Vehicle for TEI | Contract awarded by Q1 2013 | Q1-Q4 | n.a | n.a | n.a | TEI | Secuirty,EWT, ICT, Development Partners
|  | Supply of First Aid Boxes to all the 8812 Registration Areas of the Federation & 100 boxes in the HQ for the 2015 General Election. | Award of contract by Q4 2014 | n.a | Q4 | n.a | n.a | EWT | Health Services, Proc,LS
|  | Procurement of office equipments and consumbales | Approval secured and award of contract by Q1 each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Proc | F/A
5.6 | Implant the new strategy | Interative sessions with Hqrs and States Staff on the content of the Strategic and Action Plans | Interactive sessions by Q4 2012 | n.a | n.a | n.a | n.a | Commission | All Departments & State Offices
|  | Making copies of the Plan Document available to Members of the Commission and Staff | Copies to be made available by Q1 2013 | Q1 | n.a | n.a | n.a | Commission | All Departments & State Offices
|  | In-house Seminars/workshops for Members of the Commission and Staff on the Strategic Plan Actions | Approval secured by Q1each year | Q1 | Q1 | Q1 | Q1 | Commission | All Departments & State Offices
5.7 | Implement the new strategy | Heaquarters and State offices to meticulously implement the Plan | Identification and adjustment of variance done quarterly each year | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Commission | All Departments & State Offices
5.8 | Evaluate the strategy | Creation of evaluation template by the Implementation Team | Template ready by Q1 2013 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | All Departments & State Offices
|  | Regular evaluation of plan by Planning and Monitoring Directorate | Evaluation done and report presented bi-annually | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | PM | All Departments & State Offices
|  | Evaluation and review of service delivery in the Commission | Approval secured by Q4 each year | Q4 | Q4 | Q4 | Q4 | ADM | All Departments & State Offices

## Sheet2
INDEPENDENT NATIONAL ELECTORAL COMMISSION
SUMMARY OF COST YEARLY ON STRATEGIC ACTION PLAN
| 2013 | 2014 | 2015 | 2016 | TOTAL
1. Objective One | 23836429998 | 49231875582 | 23800491583 | 13598977890 | 110467775053
2. Objective Two | 4463617000 | 4890417000 | 3894800000 | 2376000000 | 15624834000
3. Objective Three | 977500000 | 1087500000 | 1067500000 | 927500000 | 4060000000
4. Objective Four | 2102725000 | 2260850000 | 2100850000 | 1840125000 | 8304550000
5. Objective Five | 15214285000 | 14619377800 | 12231311731 | 12231311731 | 54296286262
TOTAL | 46594556998 | 72090020382 | 43094953314 | 30973914621 | 192753445315

## Sheet3
S/N | OBJECTIVES | ACTIVITIES | INDICATORS | TIME FRAME |  |  |  | INDICATIVE BUDGET |  |  |  | IMPLEMENTING DEPT(S)
|  |  |  | 2013 | 2014 | 2015 | 2016 | 2013 | 2014 | 2015 | 2016 | LEAD | COLLABORATING